## BUG_File
Bug ID | Title/Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reporter & Date | Assigned To | Environment | Attachments/References
BUG-CART-001 | Inaccurate installment calculation logic | The system calculates installment totals that are mathematically inconsistent with the listed cash price. | 1. Navigate to the Products page. 2. Select a product with an installment offer (e.g., iPhone 11 Pro). 3. Add to cart and compare the "Installment Text" vs. "Subtotal". | Installment totals (e.g., $233 x 3) should logically align with the cash price ($399) | Calculated installment total ($699) is significantly higher than the cash price ($399). | Critical | High | New | Nada - 11/04/2026 | Backend Team | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com" | Links or filenames for screenshots, videos, or logs
BUG-CART-002 | Cart synchronization failure across tabs | Items added to the cart in one browser tab do not sync with other open tabs of the same session. | 1. Open the site in Tab A and add an item. 2. Open the site in Tab B. 3. Refresh Tab B and check the cart contents. | The cart and bag icon counter should be identical across all tabs after a refresh. | Cart items in Tab A are missing in Tab B; sessions remain isolated per tab. | Major | Medium | New | Nada - 11/04/2026 | Frontend Team | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-CART-003 | Cart items persist across different users on the same device | Items added to the cart by one user remain visible when a different user logs in on the same device. This causes the second user to see the previous user’s cart contents instead of their own. | 1. Login with any user(e.g.,demouser) and add at least one item to the cart 2.Logout , then login with another user (e.g.,fav_user) 3.Open the cart drawer and check the products | The cart of the second user (fav_user) contains the items added in the previous session for the same user | The cart of the second user(fav_user) contains the same products added by first user(demouser) | Critical | High | New | Yara - 16/04/2026 | Backend Team | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-CART-004 | There is no max limit on the quantity of the product purchased | There in no max limit on the quantity of products purchased or a track of how many items are remaining in stock | 1. Login with any user and add at least one item to the cart 2.Increase an item's quantity till it reaches a large number (e.g.,500) | An error message indicating a large number (e.g.,Item out of stock) or (e.g. Max limit has been reached) | The quantity keeps increasing without a certain limit | High | High | New | Yara - 16/04/2026 | Backend Team + Frontend Team | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-Tabs-001 | Favourites are updated through different sessions | Adding/Removing from favourites isn't updated for different sessions of the same user | 1. Login with (fav_user) that has 5 items in favourites by default 2.Remove / add items from favourites 3.Logout 4.Login again with (fav_user) and check the favourites | Items in the favourites are updated based on the changes made in the previous session of (fav_user) | The favourites are reset to the default favourites of (fav_user) | High | Medium | New | Yara - 16/04/2026 | Backend team | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_001 | Checkout completes without selecting payment method | The system allows users to place an order without selecting or displaying any payment method. | Add items to cart Proceed to checkout Enter valid user details Click "Place Order" | User must select a payment method before placing the order | Order is placed successfully without selecting any payment method | critical | High | New | Nour Mohamed (4/13/2026) | Backend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_002 | First Name field accepts numeric input | The First Name field does not validate input and allows numeric values. | Enter numeric value in First Name Complete checkout | Only alphabetic characters should be accepted | Numeric input is accepted and order is placed | Minor | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_003 | Last Name field accepts numeric input | The Last Name field allows numeric values without validation. | Enter numeric value in Last Name Complete checkout | Only alphabetic characters allowed | Numeric input accepted | Minor | high | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_004 | Postal Code field accepts alphabetic input | Postal Code field lacks format validation and accepts letters. | Enter letters in Postal Code Submit | Only numeric format allowed | Letters accepted | Major | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_005 | Address field accepts invalid numeric-only values | The system allows unrealistic address formats without validation. | Enter numbers only in Address Submit | Valid address format required | Numeric-only input accepted | Minor | medium | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_006 | State field accepts numeric values | State field does not validate input and accepts numbers. | Enter numeric value in State Submit | Only text values allowed | Numbers accepted | Minor | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_007 | Input fields accept extremely long values | The system does not enforce maximum length validation for input fields. | Enter very long input (1000+ characters) Submit | Input length should be restricted | Long input accepted | Major | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_008 | Input fields accept special characters | All fields accept special characters without validation. | Enter special characters in fields Submit | Special characters should be restricted or validated | Special characters accepted | Major | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_009 | Fields accept whitespace-only input | System allows empty spaces as valid input. | Enter spaces only in fields Submit | Whitespace-only input should be rejected | Accepted as valid | Major | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_010 | Refreshing confirmation page generates new orders | Refreshing the page after checkout creates new orders with different IDs. | Complete checkout Refresh page multiple times | No new orders should be created | New order generated on each refresh | Critical | High | New | Nour Mohamed (4/13/2026) | Backend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_011 | Checkout page displays total only without order details | Checkout page does not display product details or breakdown. | Add items to cart Go to checkout | Full order summary should be displayed | Only total amount shown | Major | High | New | Nour Mohamed (4/13/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_012 | customers information is not displayed in the order confirmation receipt | Customers information is not displayed in the order confirmation receipt as orders ID , Name and address | add items to cart Go to checkout page complete order go to order confirmation receipt observe customers information | Customers information:Name-order ID-Address | Customers information is not displayed in the order confirmation receipt | Critical | High | New | Mariam Tamer(13/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG_CHECKOUT_013 | Past oreders details are not displayed correctly | past order subtotal is wrong recent order delivered date is wrong | add items to cart Go to checkout page complete order go to orders field and observe details | Past orders details are desplayed correctly | past order subtotal is wrong recent order delivered date is wrong | Major | High | New | Mariam Tamer(13/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-AUTH-001 | Incorrect validation message for short username | System shows incorrect error message for short username | 1. Enter short username 2. Enter valid password 3. Click login | Show username length validation message | Shows generic invalid username message | Medium | High | Open | Maya Medhat (17/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-AUTH-002 | System accepts invalid username format | Invalid username format is accepted | Enter invalid username format and login | Validation error | Login proceeds | High | High | Open | Maya Medhat (17/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-AUTH-003 | Invalid credentials handled incorrectly | System does not properly reject wrong credentials | Enter wrong username/password | Error + prevent login | Login allowed or wrong message | Critical | High | Open | Maya Medhat (17/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-AUTH-004 | Missing validation for empty fields | Login allowed with empty fields | Leave fields empty and click login | Required fields message | No validation | High | High | Open | Maya Medhat (17/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-AUTH-005 | Requirement REQ-LOGIN-007 not enforced | System does not meet requirement | Execute testcase steps | Matches requirement | Mismatch | Medium | Medium | Open | Maya Medhat (17/4/2026) | Frontend Developer | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
BUG-Tabs-001 | Favourites are updated through different sessions | Adding/Removing from favourites isn't updated for different sessions of the same user | Steps to Reproduce | Items in the favourites are updated based on the changes made in | The favourites are reset to the default favourites of (fav_user) | High | Medium | New | Yara - 16/04/2026 | Backend team | OS: Windows 11 / Browser: Google Chrome (Latest Version) / URL: "https://bstackdemo.com"
the previous session of (fav_user)
BUG-FILTER-001 | Search results overlap with vendor filters incorrectly | The product list displays items that do not match the selected vendor filter when a search term is active. | Open the website https://bstackdemo.com | The list should show "0 Product(s) found" or only Google products if they match the search. | iPhone products (Apple) are still displayed even though the "Google" filter is selected. | Major | High | New | Mariam-19/4/2026 | Frontend Team | Windows 11 / Browser: Google Chrome / URL: https://bstackdemo.com
Type "iPhone" in the search bar.
Select "Google" from the Vendor filter on the left.